## Slide 1
RAMCO HCM Project kick off
for
Sanmina Corporation
03rd May 2018

## Slide 2
Implementation Scope
Implementation Plan
Project Management & Control
Objectives
Roles and Responsibilities
Implementation Methodology
Key Success Factors

## Slide 3
Roles and Responsibilities
Implementation Plan
Project Management & Control
Objectives
Implementation Scope
Implementation Methodology
Key Success Factors

## Slide 4: Objectives
To implement best in class, Payroll System to meet Business requirements of Sanmina
To implement robust On premise product that can help replace current manual/semi automated processing model.
Employee portal to provide ease of access to employees to perform day to day operational and strategic HR transactions.
To achieve substantial reduction in manual computations, processing, resource tracking time and elimination of redundant processes.

## Slide 5
Implementation Scope
Implementation Plan
Project Management & Control
Roles and Responsibilities
Implementation Methodology
Key Success Factors
Objectives

## Slide 6
Implementation scope
Leave
Management
Core HR
Time & Attendance
ESS(Employee Self services)
Leave Setup
Leave Definition
Leave Administration & Applying Leave
Organization
Management and Personnel Information
Movements &
Exit Management
Benefits
Administration
Schedule
Management
Paid Time-Off
Management
Time Entry
Management
Absence &
Overtime Tracking
Data Uploads
Advanced
Reporting
Mobility
Role-based
Access
Extension
Toolkit
SOA-based
Integration
Workflow
Enterprise Add-ons
Employee & Manager Self-Service
Payroll
Country-specific
Compliance
Gross & Net
Pay Calculation
Retroactive Pay
& Increments
Direct Deposit
Automation

## Slide 7: Implementation Approach
Implementation Services | Training | Data Upload
Solution Definition Configuration of business rules/workflow/ validations Deployment of product Training Master data and Opening balances upload Testing and Go live support Project Management | Approach Train the Trainer(Core User) Levels of Training Detailed training – Before user acceptance testing Administration training | Data to be Uploaded. Employee data will be migrated Leave Balance Other Balances Sanmina to provide clean and verified data in specific formats provided by RAMCO for uploading.

## Slide 8
Implementation Scope
Implementation Plan
Project Management & Control
Objectives
Roles and Responsibilities
Implementation Methodology
Key Success Factors

## Slide 9: Implementation methodology
Project Management
UAT
(On-Site)
Project Initiation
(On-Site)
Process & Policy Understand
(On-Site)
Engineering
(Off-site)
Training
(On-Site)
Go – Live
(On-Site)
Parallel Run
(On-Site)
DM
Source Target Mapping
Data
Upload
Activities
Parallel
Run
Support

## Slide 10: Project Initiation
Core Team Formation
Strategy & Planning
Project Plan
Kick off - Project Plan Sign off
Project Initiation
(On-Site)
Solution Definition
(On-Site)
Engineering
(Off-Site)
Training
(On-Site)
UAT
(On-Site)
Parallel Run
(On-Site)
Go – Live
(On-Site)

## Slide 11: Project Initiation – Project Plan
Finalization of Project Plan
  Prerequisite for starting all other activities
  To take Resource Availability into account
  Includes
    Work Break-down Structure
    Start & End dates for activities
    Activity Dependencies
    Resource Requirements

## Slide 12
Rule finalization for configurable entities
Presentation of Solution Definition Document (SDD)
Training on Master Data Collection Formats (MDCF)
Freezing on Test Scenarios for UAT
Training on Test case formats
Feedback Incorporation
Solution Definition Document
Master Data Collection Format Templates
Test Case Formats
Solution Definition
Project Initiation
(On-Site)
Solution Definition
(On-Site)
Engineering
(Off-Site)
Training
(On-Site)
UAT
(On-Site)
Parallel Run
(On-Site)
Go – Live
(On-Site)
Contd…

## Slide 13
Role of Amitysoft
  Amitysoft Model is used for detailed discussions with the Process Owners for Business Process Study.
  Classify the Business Scenarios based on business criticality and frequency of usage.
  Analyze the detailed steps in each process.
  Map the solution to RamcoHCM software and recommend the process steps.
  Identify and analyze gaps and sign-off on Personalization.
  Discuss, Review and Finalize the Enterprise model.
  Discuss, Review and Finalize the structure of the Masters for which Data collection is required.
Solution Definition
Contd…

## Slide 14
Expectations from Sanmina
  Quality time of the User champions having knowledge and expertise of current and proposed business process.
  Review and accept the recommended solution given by Amitysoft Business Analyst.
  Identification of data sources for each process.
Solution Definition

## Slide 15
Rule writing
Application configuration
Customizations
`Configured application
Final set of Usage test scenarios
Engineering
Project Initiation
(On-Site)
Solution Definition
(On-Site)
Engineering
(Off-Site)
Training
(On-Site)
UAT
(On-Site)
Parallel Run
(On-Site)
Go – Live
(On-Site)
Contd…

## Slide 16
Role of Amitysoft
  Application configuration
  Rule configurations
  Deploying the configured application on Premise
Expectations from Sanmina
  Completion of Master data collection
  Providing usage scenarios for application verification
Engineering

## Slide 17
Core user Training
Training Handouts
Training Attendance and Feedback forms
Training
Project Initiation
(On-Site)
Solution Definition
(On-Site)
Engineering
(Off-Site)
Training
(On-Site)
UAT
(On-Site)
Parallel Run
(On-Site)
Go – Live
(On-Site)
Contd…

## Slide 18
Role of Amitysoft
  Administration Training
  Training user champions
Expectations from Sanmina
  100% Attendance to Training
  Feedback
Training

## Slide 19
User Acceptance Testing
UAT Signoff
UAT
Project Initiation
(On-Site)
Solution Definition
(On-Site)
Engineering
(Off-Site)
Training
(On-Site)
UAT
(On-Site)
Parallel Run
(On-Site)
Go – Live
(On-Site)
Contd…

## Slide 20
Role of Amitysoft
  Hand holding to users.
  Resolving issues while UAT.
Expectations from Sanmina
  Test the product as per the test scenarios decided.
  Any new requirement at UAT Stage should be approved by Project Manager of both sides and considered as change request.
UAT

## Slide 21
Data Upload
Verify Payroll Outputs
Simulation of Live run
Live System Ready
Parallel Run
Project Initiation
(On-Site)
Solution Definition
(On-Site)
Engineering
(Off-Site)
Training
(On-Site)
UAT
(On-Site)
Parallel Run
(On-Site)
Go – Live
(On-Site)
Contd…

## Slide 22
Role of Amitysoft
  Set up the system for Parallel run.
  Support user champions for training to the extended end user group.
  Support data upload for carrying out the Parallel run.
  Support the user champions during Parallel run.
  Resolve application issues (if any).
Parallel Run
Contd…

## Slide 23
Expectations from Sanmina
  Ready with usage scenarios for the Parallel run
  Provide data in pre-defined templates
  Identification of user group for training/hands on
  Data upload for Parallel run.
  Provide first level support to user group
  Verifying the data and output
Parallel Run

## Slide 24
Setup for Live Usage
Live Transactions
Live System Ready
Go Live
Project Initiation
(On-Site)
Solution Definition
(On-Site)
Engineering
(Off-Site)
Training
(On-Site)
UAT
(On-Site)
Parallel Run
(On-Site)
Go – Live
(On-Site)
Contd…

## Slide 25
Role of Amitysoft
  Set up the System for Go-Live
  Support the user champions during Live run
  Resolve application issues (if any)
  Support data upload for carrying out the Live Run
Expectations from Sanmina
  Upload data into the production server (Incremental)
  Equip to carry out the first level support to end users
  Report issues(if any) through the support system (ITS)
  Live Run Commencement Certificate sign off
Go Live

## Slide 26
Project handed over to support after successful implementation.
Approach
  First level support by user champions / internal help desk.
  Second level support by RAMCO support team through ITS.
Post Live Support

## Slide 27
Implementation Scope
Implementation Plan
Project Management & Control
Objectives
Roles and Responsibilities
Implementation Methodology
Key Success Factors

## Slide 28
Project Governance
Sanmina
Project Sponsor
Sanmina
Sanmina
Project Manager
Sanmina
Process Owners & Core User Champions
Amitysoft
Project Team Consultants
Amitysoft Project Delivery Manager
Project Sponsor
Steering Committee
Operating Committee
Project Team

## Slide 29
Project Organization
Project Sponsor
Project Manager
Process Owner / Champions
IT / Technical Team ( If required)
End User
Project Delivery Manager
Project Lead / Coordinator
Functional Consultants
Off-Shore Delivery Team
Technical Lead
Sanmina
Amitysoft

## Slide 30
Project Sponsor <Employee Name>
Project Manager <Employee Name>
Amitysoft
On-Site:
User Champions <Employee Name>
Sanmina
Project Lead: Mr.JayaPrashanth
Off-Site:
Technical Consultant: Ms.Niraikalai
Project Delivery Manager: Ms.Bhuvana
Business Analyst: Mr. Praveen Kumar
Tech Lead: Mr.Muruganandam
Project Team – Key Resources
Notes: 30

## Slide 31: Management Steering Committee
The responsibilities of the Steering Committee are as follows:
  Provide overall guidance and direction to the project teams to ensure successful completion of the project.
  Decide on critical issues related to the project that have been escalated by various teams, within Sanmina, participating in the project execution.
  Conduct periodic reviews (Milestone/Monthly) of project progress and take mid-course corrective actions.
  Remove bottlenecks in the smooth progress of the project in areas such as infrastructure, resources etc.

## Slide 32: Roles and Responsibilities
Sanmina Project Manager
  Primary contact from Actives
  Ensure participation of Process champions.
  Conduct periodic weekly review with Amitysoft Project team.
  Make decisions on issues related to project and if required escalate to MSC.
  Arrange for infrastructure and facility to carryout the Project.
  Ensure Completion of project in Scheduled period.
Contd…

## Slide 33: Roles and Responsibilities
Amitysoft Project Manager
  Define responsibility for consultants.
  Coordinate with consultants for filtering issues critical to the project..
  Provide Status report to Both Project team
  Analyze and provide resolution towards the issues brought out by Project team.
  Ensure Completion of project in Scheduled period.
Contd…

## Slide 34: Roles and Responsibilities
User Champions
  Provide inputs to Amitysoft Business Analyst and play lead role in define processes.
  Evaluate the solutions proposed by Amitysoft Business Analyst.
  Participate in defining and gathering master data for their area.
  Participate in user Champion training and subsequently train the end user.
  Participate in the project reviews done by the Project Manager.
  Ensure completion of Project in Schedule.
Contd…

## Slide 35: Roles and Responsibilities
Amitysoft Business Analyst
  Understand customer business goals and objectives to be achieved from the system.
  Define business process solutions that align with customer business requirements
  Ensure delivery of the right solutions by reviewing and validating with user champions.
  Conduct training to user champions on final configured solutions.
  Identify and collate issues and work with the Project Manager to resolve these.
  Drafting daily timesheets and weekly status reports to reflect the current stage of the project and share with the stake holders.

## Slide 36
Implementation Scope
Implementation Plan
Project Management & Control
Objectives
Roles and Responsibilities
Implementation Methodology
Key Success Factors

## Slide 37: Project Schedule
* This will be refined based on the Initial Business Process Study & subsequently after the Solution Definition

## Slide 38
Implementation Scope
Implementation Plan
Key Success Factors
Objectives
Roles and Responsibilities
Implementation Methodology
Project Management & Control

## Slide 39
Project Control
Communication Mechanism
  Minutes of Meeting for all the discussions
  Weekly review meetings and weekly status reports
  Review and update project plan on each milestone completion
  Daily activity plan for subsequent week
Progress monitoring
  Project teams - weekly reviews
  Management committee (milestone reviews)
  Steering committee (phase level reviews)
Escalation
  Team member-project manager-steering committee

## Slide 40
Implementation Scope
Implementation Plan
Project Management & Control
Objectives
Roles and Responsibilities
Implementation Methodology
Key Success Factors

## Slide 41: Key Success Factors
Personal
Commitment
Decision making
Quality of data
Stick to Std Solution
Open
Communication
Adherence to Schedule

## Slide 42
Thank You
All the best
for successful Implementation!!